## UserStory
User Story Name | Description | Acceptance Criteria | Validations | Task List | Time for each task (hr) | Story Point (1 SP = 8 hrs) | Estimated Time | Actual time taken | Start Date | End Date | Owner | Task Status | Comments
Login | User can be able to login with the username and password field. | User must be able to see the login page and enter the username and password to login to the application. If the user forgets the password, he/she can click on the Forget Password link and can reset the password. | If the user is not registered then a message will be promted that the login is invalid. If the login details are correct then the user will be logged in to the application. | 1. UI Creation of Login page | 2 | 1 | 8 |  | 30/01/2020 | 30/01/2020 | Harshita Gupta | WIP
|  |  |  | 2. Create login method in Controller class. | 1
|  |  |  | 3. Create login method in Service layer. | 1
|  |  |  | 4. Create authentication and login method in DAO | 1
|  |  |  | 5. Create test cases for user validations. | 3
Sign Up | User must enter the registration details that will be stored in the database. | User must be able to enter a valid name, username, email, contact no., password and confirm password. The valid details will be stored in the database. | All the fields must be valid. Name will contain only alphabets and spaces. Username can contain alphabets and numbers. Email must contain a valid email. Contact no. must be 10 digit number and can contain only numbers. Password can contain alphabets, numbers, @, underscore and must be greater than 8 characters. Confirm password must be same as the password field. | 1. UI Creation of Register page | 2 | 1 | 8 |  | 31/01/2020 | 31/01/2020 | Harshita Gupta | WIP
|  |  |  | 2. Create user entity class and identity table in databse. | 1
|  |  |  | 3. Create register method in Controller class. | 1
|  |  |  | 4. Create register method in Service layer. | 1
|  |  |  | 5. Create register and authentication method in DAO | 1
|  |  |  | 6. Create test cases for user validations. | 2
Café Details | This module will contain the details of the café like café name, café location, café owner, café rating, café image. The admin will be able to manage the café details and the employees can view the café based on location. | User will be able to view the café datails by selecting their location from the dropdown. They can also give ratings and review to the cafes. | When the admin will add a café he must enter the valid details. Café name should contain alphabets and spaces. Café location and owner field is mandatory. | 1. UI Creation of Cafe page | 3 | 2 | 16 |  | 2020-03-02 | 2020-04-02 | Akash Verma
|  |  |  | 2. Create Cafe entity class | 1
|  |  |  | 3. Create methods to perform CRUD operations in Controller class. | 4
|  |  |  | 4. Create corresponding methods in Service layer. | 2
|  |  |  | 5. Create methods in DAO | 2
|  |  |  | 6. Create test cases for cafe details validations. | 4
Café Menu | This module will contain the menu of a particular café. The fields here are name, type and price of the item. | User will be able to view the menu of the selected café. They can add the item to the cart. | When the admin will add a menu he must enter the valid details. Item name should contain alphabets and spaces. Item type and price field is mandatory. | 1. UI Creation of Menu page | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Akash Verma
|  |  |  | 2. Create Menu entity class | 1
|  |  |  | 3. Create methods to perform CRUD operations in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO | 1
|  |  |  | 6. Create test cases for cafe item details validations. | 2
Order | All the orders made by the employee will be displayed on the page. | Employees can place the order by selecting the items from the menu and putting them in the cart. | Employees must order item with minimum one quantity. | 1. UI Creation of Cart page | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Desha Nayak
|  |  |  | 2 Create order entity class | 1
|  |  |  | 3. Create methods to add/delete or fetch all orders in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO. | 1
|  |  |  | 6. Create test cases for valid orders. | 2
Review | Employee can add review for the cafes which can be later viewed by the admin. | Employee can add star ratings and reviews for the cafes. | Review can contain more than one character. The ratings are out of 5. | 1. UI Creation of reviews. | 2 | 1 | 8 |  | 2020-04-02 | 2020-04-02 | Desha Nayak
|  |  |  | 2. Create reviews entity class | 1
|  |  |  | 3. Create methods to add/view feedbacks in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO | 1
|  |  |  | 6. Create test cases for review validations. | 2
Help Desk | There will be a ticketing service where admin can resolve the tickets raised by the employees. | Employees can raise a ticket for any queries. They can enter the query in a text box and can submit it. | User cannot submit an empty query text. | 1. UI Creation of Help Desk page | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Sujay Sail
|  |  |  | 2. Create HelpDesk entity class. | 1
|  |  |  | 3. Create methods to raise/resolve tickets in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO | 1
|  |  |  | 6. Create test cases for valid tickets. | 2
Social Media Integration | User can login through social media sites. | There will be other login or register options like Google and Facebook. | If the user is not found then it will show invalid login. | 1. UI Creation of social interaction tabs. | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Harshita Gupta
|  |  |  | 2. Create methods to login using social platforms in Controller class. | 1
|  |  |  | 3. Create login method in Service layer. | 1
|  |  |  | 4. Create authentication and login method in DAO | 1
|  |  |  | 5. Create test cases for user validations. | 3
Payment Transactions | Employees will be provided with the payment option for the items selected in the menu. | Employees can pay for the items through payment gateways. | There should be proper authentication for the payment gateways. | 1. UI Creation of payment page. | 2 | 1 | 8 |  | 2020-06-02 | 2020-06-02 | Sujay Sail
|  |  |  | 2. Create payment entity class. | 1
|  |  |  | 3. Create payment methods in Controller class. | 1
|  |  |  | 4. Create payment method in Service layer. | 1
|  |  |  | 5. Create payment method in DAO | 1
|  |  |  | 6. Create test cases for valid payments. | 2

## Supriya
User Story Name | Description | Acceptance Criteria | Validations | Task List | Time for each task (hr) | Story Point (1 SP = 8 hrs) | Estimated Time | Actual time taken | Start Date | End Date | Owner | Comments
Order | All the orders made by the employee will be displayed on the page. | Employees can place the order by selecting the items from the menu and putting them in the cart. | Employees must order item with minimum one quantity. | 1. UI Creation of Cart page | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Supriya Pawar
|  |  |  | 2 Create order entity class | 1
|  |  |  | 3. Create methods to add/delete or fetch all orders in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO. | 1
|  |  |  | 6. Create test cases for valid orders. | 2
Review | Employee can add review for the cafes which can be later viewed by the admin. | Employee can add star ratings and reviews for the cafes. | Review can contain more than one character. The ratings are out of 5. | 1. UI Creation of reviews. | 2 | 1 | 8 |  | 2020-04-02 | 2020-04-02 | Supriya Pawar
|  |  |  | 2. Create reviews entity class | 1
|  |  |  | 3. Create methods to add/view feedbacks in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO | 1
|  |  |  | 6. Create test cases for review validations. | 2

## Harshita
User Story Name | Description | Acceptance Criteria | Validations | Task List | Time for each task (hr) | Story Point (1 SP = 8 hrs) | Estimated Time | Actual time taken | Start Date | End Date | Owner | Comments
Login | User can be able to login with the username and password field. | User must be able to see the login page and enter the username and password to login to the application. If the user forgets the password, he/she can click on the Forget Password link and can reset the password. | If the user is not registered then a message will be promted that the login is invalid. If the login details are correct then the user will be logged in to the application. | 1. UI Creation of Login page | 2 | 1 | 8 |  | 30/01/2020 | 30/01/2020 | Harshita Gupta
|  |  |  | 2. Create login method in Controller class. | 1
|  |  |  | 3. Create login method in Service layer. | 1
|  |  |  | 4. Create authentication and login method in DAO | 1
|  |  |  | 5. Create test cases for user validations. | 3
Sign Up | User must enter the registration details that will be stored in the database. | User must be able to enter a valid name, username, email, contact no., password and confirm password. The valid details will be stored in the database. | All the fields must be valid. Name will contain only alphabets and spaces. Username can contain alphabets and numbers. Email must contain a valid email. Contact no. must be 10 digit number and can contain only numbers. Password can contain alphabets, numbers, @, underscore and must be greater than 8 characters. Confirm password must be same as the password field. | 1. UI Creation of Register page | 2 | 1 | 8 |  | 31/01/2020 | 31/01/2020 | Harshita Gupta
|  |  |  | 2. Create user entity class and identity table in databse. | 1
|  |  |  | 3. Create register method in Controller class. | 1
|  |  |  | 4. Create register method in Service layer. | 1
|  |  |  | 5. Create register and authentication method in DAO | 1
|  |  |  | 6. Create test cases for user validations. | 2
Social Media Integration | User can login through social media sites. | There will be other login or register options like Google and Facebook. | If the user is not found then it will show invalid login. | 1. UI Creation of social interaction tabs. | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Harshita Gupta
|  |  |  | 2. Create methods to login using social platforms in Controller class. | 1
|  |  |  | 3. Create login method in Service layer. | 1
|  |  |  | 4. Create authentication and login method in DAO | 1
|  |  |  | 5. Create test cases for user validations. | 3

## Akash
User Story Name | Description | Acceptance Criteria | Validations | Task List | Time for each task (hr) | Story Point (1 SP = 8 hrs) | Estimated Time | Actual time taken | Start Date | End Date | Owner | Task Status | Comments
Café Details | This module will contain the details of the café like café name, café location, café owner, café rating, café image. The admin will be able to manage the café details and the employees can view the café based on location. | User will be able to view the café datails by selecting their location from the dropdown. They can also give ratings and review to the cafes. | When the admin will add a café he must enter the valid details. Café name should contain alphabets and spaces. Café location and owner field is mandatory. | 1. UI Creation of Cafe page | 3 | 2 | 16 |  | 2020-03-02 | 2020-04-02 | Akash Verma | WIP | Learning about mockito and Junit to write test cases.
|  |  |  | 2. Create Cafe entity class | 1 | [6 empty] | Done
|  |  |  | 3. Create methods to perform CRUD operations in Controller class. | 4 | [6 empty] | Done
|  |  |  | 4. Create corresponding methods in Service layer. | 2 | [6 empty] | Done
|  |  |  | 5. Create methods in DAO | 2 | [6 empty] | Done
|  |  |  | 6. Create test cases for cafe details validations. | 4 | [6 empty] | WIP
Café Menu | This module will contain the menu of a particular café. The fields here are name, type and price of the item. | User will be able to view the menu of the selected café. They can add the item to the cart. | When the admin will add a menu he must enter the valid details. Item name should contain alphabets and spaces. Item type and price field is mandatory. | 1. UI Creation of Menu page | 3 | 2 | 16 |  | 2020-05-02 | 2020-06-02 | Akash Verma | Done
|  |  |  | 2. Create Menu entity class | 1 | [6 empty] | Done
|  |  |  | 3. Create methods to perform CRUD operations in Controller class. | 4 | [6 empty] | Done
|  |  |  | 4. Create corresponding methods in Service layer. | 2 | [6 empty] | Done
|  |  |  | 5. Create methods in DAO | 2 | [6 empty] | Done
|  |  |  | 6. Create test cases for cafe item details validations. | 4 | [6 empty] | WIP

## Sameer
User Story Name | Description | Acceptance Criteria | Validations | Task List | Time for each task (hr) | Story Point (1 SP = 8 hrs) | Estimated Time | Actual time taken | Start Date | End Date | Owner | Task Status | Comments
Help Desk | There will be a ticketing service where admin can resolve the tickets raised by the employees. | Employees can raise a ticket for any queries. They can enter the query in a text box and can submit it. | User cannot submit an empty query text. | 1. UI Creation of Help Desk page | 2 | 1 | 8 |  | 2020-05-02 | 2020-05-02 | Sammer Mandavia
|  |  |  | 2. Create HelpDesk entity class. | 1
|  |  |  | 3. Create methods to raise/resolve tickets in Controller class. | 1
|  |  |  | 4. Create corresponding methods in Service layer. | 1
|  |  |  | 5. Create methods in DAO | 1
|  |  |  | 6. Create test cases for valid tickets. | 2
Payment Transactions | Employees will be provided with the payment option for the items selected in the menu. | Employees can pay for the items through payment gateways. | There should be proper authentication for the payment gateways. | 1. UI Creation of payment page. | 2 | 1 | 8 |  | 2020-06-02 | 2020-06-02 | Sammer Mandavia
|  |  |  | 2. Create payment entity class. | 1
|  |  |  | 3. Create payment methods in Controller class. | 1
|  |  |  | 4. Create payment method in Service layer. | 1
|  |  |  | 5. Create payment method in DAO | 1
|  |  |  | 6. Create test cases for valid payments. | 2